## Planning Art
Week | TAAK | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | week 17 |  |  |  |  | week 18 |  |  |  |  | Week 19 |  |  |  |  | week 20 |  |  |  |  | Week 21 |  |  |  |  | week 22 |  |  |  |  | Week 23 |  |  |  |  | week 24
Dag | AF | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v | m | d | w | d | v
MoSCoW | bar: week 22 d
Deadline | bar: week 22 d
Jonat | bar: week 22 d
Pim | bar: week 22 d
Jeen | bar: week 22 d
Richie | bar: week 22 d
Melvin
TAAK AF | bar: week 22 d
TESTEN | bar: week 22 d
VAKANTIES | bar: week 22 d
Main character | bar: week 22 d
Ren animatie | bar: Week 14 d to Week 14 d; Week 15 d; week 22 d
Slash animatie #1 | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d; week 22 d
Slash animatie #2 | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d
Slash animatie #3 | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d
Slash animatie #4 | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d
Slash animatie #5 | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d
Special effects bij het slaan | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d; week 20 d; Week 21 m; week 22 d
Texture tweaken | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d; week 22 m to week 22 d
Dood animatie (max 1 sec snel) | bar: Week 15 w to Week 15 d; Week 16 m to Week 16 d; week 22 d to week 22 w
Zombie 1 | bar: week 22 d
Loop animatie | bar: Week 14 w to Week 14 d; Week 15 d to Week 15 w; week 22 d
Sterf animatie #1 | bar: Week 15 v to Week 16 w
Sterf animatie #2 | bar: Week 16 v to week 17 w; week 22 d
Sterf animatie #3 | bar: Week 16 w to Week 16 d; week 17 m to week 17 d; week 22 d
Zombie blood effect | bar: Week 16 w to Week 16 d; week 17 m to week 17 d; Week 21 m to Week 21 w; week 22 d
Texture tweaken | bar: Week 16 w to Week 16 d; week 17 m to week 17 d; week 22 d to Week 23 m
Zombie 2 | bar: Week 21 v; week 22 d
Spring animatie | bar: Week 21 v to week 22 d
Sterf animatie #1 | bar: Week 21 v to week 22 w
Zombie 3 (Boss) | bar: Week 16 d to week 17 m; week 20 w to week 20 d; Week 21 m to Week 21 d; week 22 d
Loop animatie | bar: Week 21 w to Week 21 d; week 22 m; week 22 d
Sterf animatie #1 | bar: Week 19 m to Week 19 w; Week 21 w to Week 21 d; week 22 m; week 22 d
Sterf animatie #2 | bar: week 22 d; Week 23 m to Week 23 d
Sterf animatie #3 | bar: Week 23 m to Week 23 d
Zombie blood effect | bar: Week 21 m to Week 21 w; week 22 d
Texture tweaken | bar: week 22 d; Week 23 d; Week 23 d
Interface menu | bar: week 22 d
Start scherm | bar: Week 14 d to Week 14 d; week 20 m to week 20 w; week 22 d
Startscherm Illustraties | bar: week 20 m to week 20 d
Uitleg scherm | bar: Week 15 d to Week 15 d; week 20 d; Week 21 m to Week 21 d; week 22 d
Uitleg scherm Illustraties | bar: Week 21 d
Game over screen | bar: Week 16 m to Week 16 w; Week 21 d; week 22 m; week 22 d
Game over screen Illustraties | bar: Week 21 d to Week 21 v
Game logo | bar: Week 16 d; week 17 m to week 17 d; week 20 m
Bloodspatters | bar: week 22 d
Ingame interface | bar: week 22 d
Puntenteller | bar: Week 15 d; week 22 m to week 22 d; week 22 d
Combo teksten | bar: week 22 m to week 22 d; week 22 d
Special moves indicator | bar: week 22 d
Ingame effecten | bar: week 22 d
Slash effect | bar: week 17 w to week 17 d
Ingame layer 1 (PAD) | bar: week 22 d
Prop rotsen | bar: Week 15 d to Week 15 v; week 22 d
Weg | bar: Week 14 d; Week 15 d; week 22 d
Ingame layer 2 (Environment) | bar: week 22 d
Toren (2x) | bar: Week 15 d to Week 15 v; week 22 d
Huisje (1x) | bar: Week 15 d to Week 15 v
Hut (1x) | bar: Week 15 d to Week 15 v; week 22 d
Gong huisje (1x) | bar: Week 15 d to Week 15 v; week 22 d
Bomen | bar: Week 16 m to Week 16 d; week 22 d
Muur met poortje (2x) | bar: week 22 d
Muur zonder poortje (1x) | bar: week 22 d
Muur met toren (1x) | bar: week 22 d
Brug (1x)
Boeddha (1x) | bar: week 22 d
Boeddha altaar (1x) | bar: week 22 d
Grote trommel (1x) | bar: week 22 d
Ingame layer 3 (Background environment) | bar: week 22 d
Painting berg landschap | bar: week 17 d; week 17 d; week 22 d; Week 23 d; week 24 m to week 24 w
Painting bos landschap | bar: week 22 d
Painting fishing village environment | bar: Week 14 d; Week 15 d
Sound effects | bar: week 22 d
Slash sound | bar: week 17 w; week 22 d
Jump sound | bar: week 22 d; Week 23 w to Week 23 d
Thema liedje voor startscherm | bar: week 22 d; Week 23 w to Week 23 d
Ingame liedje (loopend) | bar: Week 19 m to Week 19 w; week 22 d
Zombie gegrom | bar: week 22 d
Combo sound effect | bar: Week 23 d
Promotie materiaal | bar: week 22 d
Facebook (Profiel foto, omslag foto) | bar: week 22 d
Wallpapers | bar: week 22 d
Artwork sheets | bar: week 22 d
Facebook/Twitter sharing options | bar: week 22 d
Highscore | bar: week 22 d
Alpha Version Programming
Working main menu | bar: Week 15 d; week 22 d
Running main character | bar: Week 14 d to Week 14 d; Week 15 w to Week 15 d; week 22 d
Attack main character #1 | bar: Week 16 w to Week 16 d; week 22 d
Looping environment (with props) | bar: Week 16 m to Week 16 d; week 22 d
Walking Zombie | bar: Week 15 w to Week 15 d; week 22 d
Death zombie | bar: week 17 m to week 17 d; week 22 d
Music and sountrack | bar: week 17 m to week 17 d
Beta Version Programming | bar: week 22 d
Zombie #1 op verschillende manieren dood | bar: Week 21 m to Week 21 d; week 22 m to week 22 d
Zombie Boss Knock Back | bar: Week 21 m to Week 21 d; week 22 m to week 22 d
Zombie Boss op verschillende manieren dood | bar: Week 21 m to Week 21 d; week 22 m to week 22 d
Slice (range aanpassen) | bar: Week 21 m to Week 21 d; week 22 m to week 22 d
Camera perspectief (tweaken) | bar: Week 21 m to Week 21 d; week 22 m to week 22 d
Menu (tweaken van snelheid fade in's) | bar: Week 21 m to Week 21 d; week 22 m to week 22 w
Sound effects | bar: Week 21 m to Week 21 d; week 22 m to week 22 d
E
S
T

## Vrije dagen
VRIJE DAGEN
JONAT | WOENSDAG
MELVIN | VRIJDAG
JEEN | VRIJDAG
PIM | DONDERDAG
RICH | VRIJDAG